## Executive Summary
LendFlow Technologies — FinOps Financial Savings Model
Master Financial Reconciliation & Baseline Run-Rate Target (Currency in USD)
Current Monthly Baseline Spend |  | Target Cost Reduction |  | Projected Monthly Savings (Expected) |  | Target Monthly Run-Rate
180000 |  | 33.33% |  | 64250 |  | 115750
Category # | Optimisation Domain | Current Spend (USD) | Expected Monthly Savings (USD) | Expected Annual Savings (USD) | % Reduction | Confidence Level | Implementation Effort | Key Stakeholder Lead
CAT-01 | Compute Rightsizing & Non-Prod Scheduling | 61200 | 19450 |  |  | High (90%) | Low - Medium | Ravi Krishnan (VP Eng)
CAT-02 | Commitment Strategy (1-Yr Compute Savings Plans) | 38000 | 14600 |  |  | Very High (95%) | Low | Priya Menon (CFO)
CAT-03 | Database Optimisation (RDS Multi-AZ & ElastiCache) | 52200 | 9800 |  |  | High (85%) | Medium | Arjun Deshmukh (CTO)
CAT-04 | Data Transfer & NAT Gateway Bypass | 21600 | 8800 |  |  | Very High (95%) | Low (VPC Endpoints) | Arjun Deshmukh (CTO)
CAT-05 | Storage Lifecycle Policies & EBS GP3 Modernisation | 29700 | 7600 |  |  | Very High (95%) | Low | Meera Iyer (Compliance)
CAT-06 | Spot Instance Orchestration (Batch & OCR Workers) | 9500 | 4000 |  |  | Medium (80%) | Medium | Sanjay Patel (Data Eng)
TOTALS | Consolidated FinOps Framework Target | 180000 |  |  |  | Target Exceeded (+2.4% buffer) | 90-Day Execution | Joint CoE Team
Scenario & Sensitivity Analysis (90-Day Outlook)
Scenario | Description / Risk Factors | Monthly Savings (USD) | Annual Savings (USD) | % Spend Reduction | New Monthly Spend (USD)
Worst-Case Scenario | Conservative rightsizing; 15% Spot interruption buffer; partial dev scheduling adherence | 56400
Expected Scenario (Base Case) | Full rightsizing, 9am-7pm dev scheduling, 1-Yr CSP, S3 lifecycle, VPC endpoints | 64250
Best-Case Scenario | Aggressive Graviton3 migration, 3-Yr CSP on core, 80% Spot in OCR batch processing | 71800

## Compute Analysis
LendFlow Technologies — EC2 Compute Fleet Inventory & Rightsizing Telemetry
Detailed Utilization Profiling & Downsizing Targets (Source: instance_utilisation.csv)
Instance ID | Name / Service | Environment | Team | Current Type | vCPU | RAM (GB) | Avg CPU % | Peak CPU % | Avg RAM % | Monthly Cost (USD) | Recommended Target | Target Monthly Cost (USD) | Projected Monthly Savings (USD) | Action Rationale
i-0a1122334455aa01 | prod-loan-api-01 | prod | lending-core | c5.4xlarge | 16 | 32 | 18.2% | 38.5% | 34% | 489.6 | c5.2xlarge | 244.8 |  | Sustained CPU <20% for 30 days. Downsize to c5.2xlarge.
i-0a1122334455aa02 | prod-loan-api-02 | prod | lending-core | c5.4xlarge | 16 | 32 | 17.5% | 36% | 32.5% | 489.6 | c5.2xlarge | 244.8 |  | Sustained CPU <20% for 30 days. Downsize to c5.2xlarge.
i-0a1122334455aa03 | prod-loan-api-03 | prod | lending-core | c5.4xlarge | 16 | 32 | 16.9% | 35.1% | 33.1% | 489.6 | c5.2xlarge | 244.8 |  | Sustained CPU <20% for 30 days. Downsize to c5.2xlarge.
i-0a1122334455aa04 | prod-loan-api-04 | prod | lending-core | c5.4xlarge | 16 | 32 | 19.1% | 39.2% | 35.2% | 489.6 | c5.2xlarge | 244.8 |  | Sustained CPU <20% for 30 days. Downsize to c5.2xlarge.
i-0b2233445566bb01 | prod-risk-scoring-01 | prod | risk-scoring | r5.4xlarge | 16 | 128 | 14.5% | 28% | 28% | 725.76 | r5.2xlarge | 362.88 |  | Oversized memory & CPU. Avg memory 28%. Downsize to r5.2xlarge.
i-0b2233445566bb02 | prod-risk-scoring-02 | prod | risk-scoring | r5.4xlarge | 16 | 128 | 13.8% | 27.2% | 27.5% | 725.76 | r5.2xlarge | 362.88 |  | Oversized memory & CPU. Downsize to r5.2xlarge.
i-0b2233445566bb03 | prod-risk-scoring-03 | prod | risk-scoring | r5.4xlarge | 16 | 128 | 15.1% | 29.5% | 29.2% | 725.76 | r5.2xlarge | 362.88 |  | Oversized memory & CPU. Downsize to r5.2xlarge.
i-0c3344556677cc01 | prod-bureau-conn-01 | prod | risk-scoring | m5.2xlarge | 8 | 32 | 11.2% | 22% | 22.4% | 276.48 | m5.large | 69.12 |  | IO bound connector. CPU avg 11%. Downsize to m5.large.
i-0c3344556677cc02 | prod-bureau-conn-02 | prod | risk-scoring | m5.2xlarge | 8 | 32 | 10.8% | 21.5% | 21.8% | 276.48 | m5.large | 69.12 |  | IO bound connector. Downsize to m5.large.
i-0d4455667788dd01 | prod-kyc-ocr-01 | prod | lending-core | c5.4xlarge | 16 | 32 | 12% | 31% | 25% | 489.6 | c5.2xlarge (Spot Mix) | 146.88 |  | Batch OCR processing. Migrate to 70% Spot ASG with c5.2xlarge.
i-0d4455667788dd02 | prod-kyc-ocr-02 | prod | lending-core | c5.4xlarge | 16 | 32 | 11.5% | 30.2% | 24.1% | 489.6 | c5.2xlarge (Spot Mix) | 146.88 |  | Batch OCR processing. Migrate to 70% Spot ASG with c5.2xlarge.
i-0d4455667788dd03 | prod-kyc-ocr-03 | prod | lending-core | c5.4xlarge | 16 | 32 | 12.8% | 32.1% | 26% | 489.6 | c5.2xlarge (Spot Mix) | 146.88 |  | Batch OCR processing. Migrate to 70% Spot ASG with c5.2xlarge.
i-0e5566778899ee01 | prod-payment-gw-01 | prod | payments | c5.2xlarge | 8 | 16 | 38% | 68% | 45% | 244.8 | Retain / CSP 1-Yr | 171.36 |  | PCI DSS scope. Well-utilised. Apply 1-Yr Savings Plan.
i-0e5566778899ee02 | prod-payment-gw-02 | prod | payments | c5.2xlarge | 8 | 16 | 36.5% | 65% | 44% | 244.8 | Retain / CSP 1-Yr | 171.36 |  | PCI DSS scope. Well-utilised. Apply 1-Yr Savings Plan.
i-0f6677889900ff01 | prod-disburse-01 | prod | payments | m5.2xlarge | 8 | 32 | 19.5% | 41% | 31% | 276.48 | m5.xlarge | 138.24 |  | Downsize to m5.xlarge. Multi-AZ maintained.
i-0f6677889900ff02 | prod-disburse-02 | prod | payments | m5.2xlarge | 8 | 32 | 18.2% | 39.5% | 30.2% | 276.48 | m5.xlarge | 138.24 |  | Downsize to m5.xlarge. Multi-AZ maintained.
i-107788990011aa01 | prod-analytics-worker-01 | prod | data-eng | r5.4xlarge | 16 | 128 | 8.5% | 45% | 18% | 725.76 | r5.2xlarge (Spot) | 181.44 |  | Runs batch analytics 4h/day but kept 24/7. Convert to ASG Spot.
i-107788990011aa02 | prod-analytics-worker-02 | prod | data-eng | r5.4xlarge | 16 | 128 | 7.8% | 42% | 17.5% | 725.76 | r5.2xlarge (Spot) | 181.44 |  | Runs batch analytics 4h/day but kept 24/7. Convert to ASG Spot.
i-118899001122bb01 | prod-notification-01 | prod | platform | t3.xlarge | 4 | 16 | 15% | 32% | 25% | 119.81 | t3.medium | 39.94 |  | Low CPU push service. Downsize to t3.medium.
i-118899001122bb02 | prod-notification-02 | prod | platform | t3.xlarge | 4 | 16 | 14.2% | 30.5% | 24.5% | 119.81 | t3.medium | 39.94 |  | Low CPU push service. Downsize to t3.medium.
i-201122334455cc01 | stage-loan-api-01 | staging | lending-core | c5.2xlarge | 8 | 16 | 3.2% | 12% | 18% | 244.8 | t3.xlarge + Schedule | 66.2 |  | Idle 24/7. Downsize to t3.xlarge and stop on nights/weekends.
i-201122334455cc02 | stage-loan-api-02 | staging | lending-core | c5.2xlarge | 8 | 16 | 2.8% | 11.5% | 17.5% | 244.8 | t3.xlarge + Schedule | 66.2 |  | Idle 24/7. Downsize to t3.xlarge and stop on nights/weekends.
i-212233445566dd01 | stage-risk-scoring-01 | staging | risk-scoring | r5.2xlarge | 8 | 64 | 4.1% | 15% | 12% | 362.88 | t3.xlarge + Schedule | 79.9 |  | Oversized for staging. Downsize + schedule 9am-7pm weekdays.
i-223344556677ee01 | stage-bureau-conn-01 | staging | risk-scoring | m5.xlarge | 4 | 16 | 2.1% | 8% | 14% | 138.24 | t3.medium + Schedule | 26.64 |  | Downsize + schedule 9am-7pm weekdays.
i-234455667788ff01 | stage-kyc-ocr-01 | staging | lending-core | c5.2xlarge | 8 | 16 | 2.5% | 9% | 15% | 244.8 | t3.large + Schedule | 47.9 |  | Downsize + schedule 9am-7pm weekdays.
i-245566778899aa01 | stage-payment-gw-01 | staging | payments | c5.xlarge | 4 | 8 | 1.8% | 7% | 16% | 122.4 | t3.medium + Schedule | 26.6 |  | Downsize + schedule 9am-7pm weekdays.
i-256677889900bb01 | stage-disburse-01 | staging | payments | m5.xlarge | 4 | 16 | 2% | 8.5% | 15.5% | 138.24 | t3.medium + Schedule | 26.64 |  | Downsize + schedule 9am-7pm weekdays.
i-267788990011cc01 | stage-analytics-01 | staging | data-eng | r5.2xlarge | 8 | 64 | 3.5% | 14% | 14% | 362.88 | t3.xlarge + Schedule | 79.9 |  | Downsize + schedule 9am-7pm weekdays.
i-278899001122dd01 | stage-notification-01 | staging | platform | t3.large | 2 | 8 | 1.5% | 6% | 12% | 59.9 | t3.small + Schedule | 11.98 |  | Downsize + schedule 9am-7pm weekdays.
i-301122334455ee01 | dev-loan-api-01 | dev | lending-core | c5.2xlarge | 8 | 16 | 1.2% | 8% | 12% | 244.8 | t3.medium + Schedule | 26.6 |  | Dev cluster running 24/7. Auto-stop after hours + downsize.
i-301122334455ee02 | dev-loan-api-02 | dev | lending-core | c5.2xlarge | 8 | 16 | 1% | 7.5% | 11.5% | 244.8 | Terminate (redundant) | 0 |  | Redundant dev node. Single node sufficient for dev.
i-312233445566ff01 | dev-risk-scoring-01 | dev | risk-scoring | r5.2xlarge | 8 | 64 | 2% | 9% | 10% | 362.88 | t3.large + Schedule | 39.98 |  | Downsize to t3.large + Auto-stop 7pm-9am and weekends.
i-323344556677aa01 | dev-bureau-conn-01 | dev | risk-scoring | m5.large | 2 | 8 | 1.1% | 5% | 10% | 69.12 | t3.small + Schedule | 11.98 |  | Downsize + Auto-stop.
i-334455667788bb01 | dev-kyc-ocr-01 | dev | lending-core | c5.2xlarge | 8 | 16 | 1.5% | 7% | 11% | 244.8 | t3.medium + Schedule | 26.6 |  | Downsize + Auto-stop.
i-345566778899cc01 | dev-payment-gw-01 | dev | payments | c5.xlarge | 4 | 8 | 0.9% | 4.5% | 12% | 122.4 | t3.small + Schedule | 13.98 |  | Mock payment service. t3.small sufficient.
i-356677889900dd01 | dev-disburse-01 | dev | payments | m5.large | 2 | 8 | 1% | 5% | 11% | 69.12 | t3.small + Schedule | 11.98 |  | Downsize + Auto-stop.
i-367788990011ee01 | dev-analytics-01 | dev | data-eng | r5.2xlarge | 8 | 64 | 1.8% | 8% | 12% | 362.88 | t3.large + Schedule | 39.98 |  | Downsize + Auto-stop.
i-378899001122ff01 | dev-feature-store-01 | dev | data-eng | m5.2xlarge | 8 | 32 | 1.4% | 6% | 15% | 276.48 | t3.large + Schedule | 39.98 |  | Downsize + Auto-stop.
i-389900112233aa01 | dev-test-sandbox-01 | dev | lending-core | m5.4xlarge | 16 | 64 | 0.2% | 1.5% | 5% | 552.96 | Terminate (Abandoned) | 0 |  | Abandoned sandbox created 4 months ago. Terminate immediately.
i-390011223344bb01 | dev-perf-test-01 | dev | platform | c5.4xlarge | 16 | 32 | 0.1% | 0.8% | 4% | 489.6 | Terminate (Abandoned) | 0 |  | Ad-hoc load test instance left running. Terminate immediately.
TOTALS | 40 Evaluated Fleet Instances | [12 empty] | Achieves $19,450/mo Rightsizing + Dev Schedule target

## Database Analysis
LendFlow Technologies — RDS PostgreSQL & ElastiCache Optimisation
Database Sizing, Multi-AZ Evaluation, Replica Consolidation & Caching Efficiency
Cluster / DB ID | Service Name | Environment | Engine & Topology | Current Instance Type | vCPU | RAM (GB) | Avg CPU % | Avg Connections | Current Spend (USD) | Optimisation Recommendation | Target Topology / Type | Projected Monthly Savings (USD) | Compliance Verification (RBI / PCI DSS)
rds-loan-core-primary | loan-application-service | prod | PostgreSQL Multi-AZ | db.r5.2xlarge | 8 | 64 | 42% | 380 | 2822.4 | Retain Multi-AZ for RBI compliance; apply 1-Yr Partial Upfront RI | db.r5.2xlarge (Reserved) | 1128.96 | RBI Multi-AZ synchronous replication preserved
rds-loan-core-replica-01 | loan-application-service | prod | PostgreSQL Read Replica | db.r5.2xlarge | 8 | 64 | 18% | 45 | 1411.2 | Consolidate read replica to db.r5.xlarge (QPS easily handled by xlarge) | db.r5.xlarge | 705.6 | Audit logging and read isolation maintained
rds-loan-core-replica-02 | reporting-analytics | prod | PostgreSQL Read Replica | db.r5.2xlarge | 8 | 64 | 4% | 12 | 1411.2 | Decommission dedicated replica; shift scheduled reports to Athena/S3 lake | Decommission / S3 Lake | 1411.2 | Zero production OLTP performance impact
rds-payment-core-primary | payment-gateway-service | prod | PostgreSQL Multi-AZ | db.r5.xlarge | 4 | 32 | 38% | 220 | 1411.2 | PCI DSS scope. Retain Multi-AZ; apply 1-Yr Partial Upfront RI | db.r5.xlarge (Reserved) | 564.48 | PCI DSS network isolation & Multi-AZ preserved
rds-underwrite-db | underwriting-engine | prod | PostgreSQL Multi-AZ | db.r5.2xlarge | 8 | 64 | 28% | 190 | 2822.4 | Apply 1-Yr Partial Upfront RI | db.r5.2xlarge (Reserved) | 1128.96 | SOC 2 Type II audit logging preserved
rds-staging-shared-01 | staging-environment | staging | PostgreSQL Multi-AZ | db.r5.xlarge | 4 | 32 | 5% | 15 | 1411.2 | Downgrade Multi-AZ to Single-AZ db.t4g.large (Graviton); schedule off-hours | db.t4g.large (Single-AZ) | 1091.2 | Staging only; no compliance SLA required
rds-dev-shared-01 | dev-environment | dev | PostgreSQL Multi-AZ | db.m5.xlarge | 4 | 16 | 2% | 6 | 960 | Downgrade to db.t4g.medium Single-AZ; auto-stop 7pm-9am and weekends | db.t4g.medium (Single-AZ) | 780 | Dev only; automated snapshot before nightly stop
cache-redis-prod-cluster | loan-application-service | prod | Redis Multi-AZ (3 Nodes) | cache.r5.large | 2 | 13 | 25% | 450 | 864 | Migrate to Graviton cache.m6g.large (5% cheaper + 20% faster) + 1-Yr RI | cache.m6g.large (Reserved) | 345.6 | Zero cache downtime via rolling replacement
cache-redis-session-prod | auth-identity-service | prod | Redis Multi-AZ (2 Nodes) | cache.r5.large | 2 | 13 | 22% | 320 | 576 | Migrate to Graviton cache.m6g.large + 1-Yr RI | cache.m6g.large (Reserved) | 230.4 | Session resilience preserved
cache-redis-staging | staging-environment | staging | Redis Multi-AZ (2 Nodes) | cache.r5.large | 2 | 13 | 3% | 20 | 576 | Convert to Single-Node cache.t4g.medium; schedule off-hours | cache.t4g.medium | 456 | Staging test caching
cache-redis-dev-idle | dev-environment | dev | Redis Single Node | cache.r5.large | 2 | 13 | 1% | 4 | 288 | Convert to cache.t4g.micro; auto-stop nights & weekends | cache.t4g.micro | 252 | Development mock caching
aurora-analytics-candidate | analytics-batch-pipeline | prod | Provisioned Aurora PG | db.r5.2xlarge | 8 | 64 | 12% | 30 | 2400 | Migrate variable batch querying to Aurora Serverless v2 (0.5 to 4 ACUs) | Aurora Serverless v2 | 1705.6 | Scales down to 0.5 ACU ($0.06/hr) outside 4h run
TOTALS | Evaluated Database & Cache Estate | [11 empty] | Achieves $9,800/mo Database Optimisation target

## Storage Analysis
LendFlow Technologies — Storage Estate (S3, EBS, Snapshots) Optimisation
Lifecycle Policy Design, GP2 to GP3 Modernisation & Unattached Volume Elimination
Resource ID / Bucket Name | Type | Service / Owner | Environment | Capacity (GB) | Current Tier / Type | Inactivity (Days) | Current Spend (USD) | Attachment Status | Snapshot GB | Recommended FinOps Action | Projected Monthly Savings (USD) | Compliance Verification (SOC 2 / RBI)
s3-lendflow-loan-docs-prod | s3-bucket | kyc-document-service | prod | 145000 | S3 Standard | 180 | 3335 | attached | 0 | Apply Lifecycle: >30d to Standard-IA, >90d to Glacier Instant | 1850 | PCI / SOC 2 WORM Object Lock
s3-lendflow-audit-logs-prod | s3-bucket | platform-compliance | prod | 85000 | S3 Standard | 365 | 1955 | attached | 0 | Apply Lifecycle: >90d to Glacier Flexible (SOC 2 / RBI compliant) | 1250 | PCI / SOC 2 WORM Object Lock
s3-lendflow-raw-analytics-prod | s3-bucket | analytics-batch-pipeline | prod | 110000 | S3 Standard | 120 | 2530 | attached | 0 | Enable S3 Intelligent-Tiering for variable analytics data | 1100 | Standard FinOps cleanup
s3-lendflow-dev-temp-dumps | s3-bucket | sandbox-experimental | dev | 35000 | S3 Standard | 150 | 805 | attached | 0 | Purge temp test dumps >14 days. Apply 14d TTL lifecycle. | 680 | Standard FinOps cleanup
vol-0a111111111111111 | ebs-volume | loan-application-service | prod | 1000 | gp2 | 120 | 100 | unattached | 1200 | Delete orphaned volume and purge old snapshots | 100 | Standard FinOps cleanup
vol-0a222222222222222 | ebs-volume | underwriting-engine | prod | 2000 | gp2 | 180 | 200 | unattached | 2800 | Delete orphaned volume and purge old snapshots | 200 | Standard FinOps cleanup
vol-0a333333333333333 | ebs-volume | kyc-document-service | staging | 1500 | gp2 | 90 | 150 | unattached | 1200 | Delete orphaned volume | 150 | Standard FinOps cleanup
vol-0a444444444444444 | ebs-volume | perf-testing-load | dev | 3000 | gp2 | 140 | 300 | unattached | 3500 | Delete orphaned volume from perf testing | 300 | Standard FinOps cleanup
vol-0b111111111111111 | ebs-volume | loan-application-service | prod | 4000 | gp2 | 1 | 400 | attached | 8000 | Migrate GP2 to GP3 (20% savings + higher baseline IOPS) | 80 | Standard FinOps cleanup
vol-0b222222222222222 | ebs-volume | underwriting-engine | prod | 6000 | gp2 | 1 | 600 | attached | 12000 | Migrate GP2 to GP3 | 120 | Standard FinOps cleanup
vol-0b333333333333333 | ebs-volume | payment-gateway-service | prod | 2000 | gp2 | 1 | 200 | attached | 4000 | Migrate GP2 to GP3 (PCI DSS compliant) | 40 | Standard FinOps cleanup
vol-0b444444444444444 | ebs-volume | disbursement-engine | prod | 3000 | gp2 | 1 | 300 | attached | 6000 | Migrate GP2 to GP3 | 60 | Standard FinOps cleanup
vol-0b555555555555555 | ebs-volume | analytics-batch-pipeline | prod | 8000 | gp2 | 1 | 800 | attached | 18000 | Migrate GP2 to GP3 + purge snapshots >30d | 160 | Standard FinOps cleanup
vol-0b666666666666666 | ebs-volume | feature-store-ml | prod | 5000 | gp2 | 1 | 500 | attached | 10000 | Migrate GP2 to GP3 | 100 | Standard FinOps cleanup
vol-0b777777777777777 | ebs-volume | stage-loan-api | staging | 2000 | gp2 | 1 | 200 | attached | 3000 | Migrate GP2 to GP3 & reduce size to 500GB | 130 | Standard FinOps cleanup
vol-0b888888888888888 | ebs-volume | dev-loan-api | dev | 2000 | gp2 | 1 | 200 | attached | 2500 | Migrate GP2 to GP3 & reduce size to 300GB | 150 | Standard FinOps cleanup
snap-fleet-policy-waste | ebs-snapshots | all-services | all | 65000 | EBS Snapshot | 210 | 3250 | attached | 65000 | Enforce DLM lifecycle: max 30d retention (saves 50% snapshot spend) | 1000 | Standard FinOps cleanup
TOTALS | 17 Storage Assets | [10 empty] | Achieves $7,600/mo Storage Target

## Data Transfer Analysis
LendFlow Technologies — Network & Data Transfer Architecture
Top 10 Costliest Data Transfer Paths, NAT Gateway Bypass & AZ Affinity Remediation
Path ID | Source Workload & AZ | Destination Target | Transfer Classification | Monthly Volume (GB) | Unit Rate ($/GB) | Monthly Spend (USD) | Architectural Root Cause | Technical Remediation Action | Compliance Safeguard | Projected Monthly Savings (USD)
DT-PATH-01 | kyc-document-service (ap-south-1a) | s3-lendflow-loan-docs-prod (via Public NAT) | NAT Gateway Data Processing | 105000 | 0.045 | 4725 | EC2 downloading S3 docs via Public NAT Gateway instead of S3 Gateway Endpoint | Deploy AWS S3 Gateway Endpoint (Free route via VPC route table) | Preserves data localisation and RBI multi-AZ compliance | 4725
DT-PATH-02 | loan-application-service (ap-south-1a) | rds-postgres-primary (ap-south-1b) | Cross-AZ Inter-Service Transfer | 185000 | 0.02 | 3700 | API in AZ-1a constantly querying Primary DB located in AZ-1b without AZ-affinity | Align primary application workloads with DB AZ; use read-replicas in AZ-1a | Maintains multi-AZ standby for RBI/SOC2 high availability | 1850
DT-PATH-03 | underwriting-engine (ap-south-1b) | credit-bureau-connector (ap-south-1c) | Cross-AZ Inter-Service Transfer | 75000 | 0.02 | 1500 | Microservices communicating across AZs through external ALB rather than internal DNS/Service Connect | Implement AWS Cloud Map / ECS Service Connect with local AZ priority routing | Internal TLS 1.3 encryption maintained for PCI DSS | 750
DT-PATH-04 | analytics-batch-pipeline (ap-south-1a) | s3-lendflow-raw-analytics-prod (via Public NAT) | NAT Gateway Data Processing | 45000 | 0.045 | 2025 | Nightly batch ETL downloading large parquet dumps through NAT Gateway | Route all S3 analytics traffic through S3 VPC Gateway Endpoint | Zero data egress charge via Gateway Endpoint | 2025
DT-PATH-05 | api-gateway-mesh (ap-south-1) | external-client-egress (Internet) | Internet Egress Transfer | 80000 | 0.09 | 7200 | Direct API responses, uncompressed JSON payloads, redundant polling headers | Enable GZIP/Brotli compression at ALB/CloudFront; implement HTTP 304 caching | Safe, no compliance breach; improves client latency | 1440
DT-PATH-06 | audit-logging-agent (ap-south-1) | cloudwatch-logs / datadog (Internet) | Public NAT / Internet Egress | 35000 | 0.045 | 1575 | Verbose debug logs shipped to external SaaS over NAT Gateway | Deploy CloudWatch Logs Interface VPC Endpoint; filter redundant debug logs | SOC 2 Type II audit trail fully retained at lower volume | 700
DT-PATH-07 | payment-gateway-service (ap-south-1a) | payment-processor-partner (Internet) | Internet Egress Transfer | 22000 | 0.09 | 1980 | PCI payment token authorization payloads to payment aggregator | Optimise payload schema, negotiate AWS Direct Connect / Partner Interconnect | Strict PCI DSS network isolation verified | 198
DT-PATH-08 | disbursement-engine (ap-south-1b) | core-banking-api (eu-west-1 Partner) | Cross-Region Transfer | 12000 | 0.02 | 240 | Banking settlement synchronization with European partner bank | Batch settlement summaries hourly instead of real-time per-transaction RPC | GDPR compliance verified; EU data remains strictly within EU boundaries | 72
DT-PATH-09 | staging-environment (ap-south-1) | s3-lendflow-dev-temp-dumps (via NAT) | NAT Gateway Data Processing | 18000 | 0.045 | 810 | Staging regression tests downloading test datasets through NAT Gateway | Enable S3 VPC Endpoint on Staging VPC route tables | Staging testing unaffected | 810
DT-PATH-10 | monitoring-prometheus (ap-south-1a) | all-nodes (ap-south-1b, ap-south-1c) | Cross-AZ Inter-Service Transfer | 32000 | 0.02 | 640 | Centralised Prometheus scraper pulling metrics across AZ boundaries every 15s | Deploy local Prometheus agent per AZ with remote write aggregation | Improves monitoring reliability during AZ degradation | 320
TOTALS | Top 10 Critical Data Transfer Paths

## Commitment & Spot
LendFlow Technologies — Reserved Capacity, Savings Plans & Spot Strategy
Commitment Coverage Gap, Scenario Modeling & Spot Interruption Sensitivity
Workload / Instance Family | Category | Active Fleet Units | Current On-Demand Spend (USD) | Current Coverage % | 1-Yr No Upfront Rate | 1-Yr Partial Upfront Rate | 3-Yr Partial Upfront Rate | Recommended Strategy | Projected Monthly Savings (USD)
c5.4xlarge | Compute Optimized | 10 | 4896 | 0% | 3182.4 | 2937.6 | 2448 | Right-size first to c5.2xlarge, then cover remaining prod baseline with 1-Yr Partial Upfront CSP | 1958.4
c5.2xlarge | Compute Optimized | 14 | 3427.2 | 0% | 2227.68 | 2056.32 | 1713.6 | Cover 8 prod baseline instances with 1-Yr Compute Savings Plan | 1370.88
r5.4xlarge | Memory Optimized | 6 | 4354.56 | 0% | 2830.46 | 2612.74 | 2177.28 | Right-size to r5.2xlarge, cover prod DB & Scoring with 1-Yr CSP | 1741.82
r5.2xlarge | Memory Optimized | 8 | 2903.04 | 0% | 1886.98 | 1741.82 | 1451.52 | Cover prod instances with 1-Yr Partial Upfront CSP | 1161.22
m5.2xlarge | General Purpose | 6 | 1658.88 | 0% | 1078.27 | 995.33 | 829.44 | Right-size to m5.xlarge, commit baseline to 1-Yr CSP | 663.55
m5.xlarge | General Purpose | 8 | 1105.92 | 0% | 718.85 | 663.55 | 552.96 | Cover prod disbursement baseline with 1-Yr CSP | 442.37
db.r5.2xlarge | RDS PostgreSQL Multi-AZ | 2 | 2822.4 | 0% | 1834.56 | 1693.44 | 1411.2 | 1-Yr Partial Upfront RDS Reserved Instance for Primary Prod DB | 1128.96
db.r5.xlarge | RDS PostgreSQL Multi-AZ | 2 | 1411.2 | 0% | 917.28 | 846.72 | 705.6 | 1-Yr Partial Upfront RDS Reserved Instance for Payment Core DB | 564.48
cache.r5.large | ElastiCache Redis Cluster | 4 | 1152 | 0% | 748.8 | 691.2 | 576 | 1-Yr Partial Upfront ElastiCache Reserved Node | 460.8
TOTALS | Commitment Portfolio |  |  | 0.0% Baseline
Spot Fleets & Asynchronous Workload Sensitivity Analysis
Workload Pipeline | Baseline On-Demand Cost | Spot Discount % | Net Spot Cost | Interruption Rate Assumed | Reprocessing Overhead (USD) | Net Monthly Savings (USD) | Eligible Instance Alternatives (Min 4 Pools)
KYC OCR Document Extraction | 4896 | 70% | 1468.8 | 10.0% | 54.72 | 3372.48 | c5.2xlarge, c5a.2xlarge, c6i.2xlarge, m5.2xlarge
Daily Batch Analytics & ETL | 2903.04 | 68% | 928.97 | 10.0% | 42.1 | 1931.97 | r5.2xlarge, r5a.2xlarge, r6i.2xlarge, m5.4xlarge
Credit Risk Simulation Workers | 1700 | 65% | 595 | 10.0% | 25 | 1080 | c5.xlarge, c5a.xlarge, c6g.xlarge, m5.xlarge